## Slide 1
ESD 5613 : Final Project (Fall 2021)
Remote communication with 8051
        Dhiraj Bennadi
        Rajat Chaple

## Slide 2: Block Diagram
Target system
Memory Backup
Power Supply
ESP8266 (uC)
Hash check
Hash key generation
SPI
UART
LCD Interface
8051 (uC)
UART
GPIO
New
New
New

## Slide 3: Software elements
New elements
  Hashing
  SPI interface
  Socket programming
  GUI (optional)
Existing elements
  UART interface
  GPIO
Hardware elements
New elements
  Power circuit
  ESP8266 (or alternative)
  External memory (e.g. SD card)
Existing elements
  8051 uController
  LCD (optional)
  Keypad (optional)

## Slide 4: Key milestones
Designing Power circuit
PCB Layout
Communication between ESP8266 and 8051
Communication between Host PC to ESP8266
Communication between ESP8266 to External memory

## Slide 5: Project deliverables
Task | Expected Due Date | Assigned to
Power Circuit design | 31st October 2021 | Rajat Chaple
Ordering of parts | 4th November | Dhiraj Bennadi
Schematic | 9th November | Both
PCB Layout | 13th November | Rajat Chaple
Interfacing UART (ESP8266 to 8051) | 14th November | Dhiraj Bennadi
Interfacing SPI (ESP8266 to Memory card) | 21st November | Both
Socket communication | 26th November | Rajat Chaple
Hashing / CRC check | 27th November | Dhiraj Bennadi
Unit Testing | 30th November | Both
System Testing | 3rd December | Both
Report | 5th December | Both

## Slide 6: Fallback plan : Automated Wire spooler
Memory Backup
Power Supply
LCD Interface
microcontroller
UART
GPIO
New
New
New
NRF Device
Actuator
(motor & cutter)